## Q1
Priority | Module | Task | Status | Sequence
P0 | UBA | UBA events | Live | 0
P0 | Jobs Tab | Job Postings | Live | 0
P0 | Login | KYC handling | Live | 0
P0 | Hard/Soft Updates | Pull back API (Forced App update popup) | Live | 0
P0 | Search option | Job postings | Live | 0
P0 | Search option | Resdex folders | Done
P0 | Search option | Inbox | WIP | 50
p0 | Dashboard | Recent Activities (All, Viewed, Called, Commented, Mailed) | WIP | 1
P1 | Dashboard | Save for later (Bookmark cv profiles) |  | 2
P1 | Comments | Adding comments on SRP, CV detail |  | 11
P1 | Dashboard | Notifications Center |  | 3
P1 | Post call feedback | Post call feedback |  | 10
P2 | Educational screens | Popups shown to guide users or explain certain features in first install |  | 6
P2 | Advance Search - More options | Functional Area, Functional role, Industry, Company, Designation, Education |  | 9
P2 | Multi select options | multiple CV selection on SRP - for Adding into folders, deleting |  | 13
P2 | RMJ | Add Job to mail/ Edit templates |  | 18
P2 | Resdex folder options | Share/Unshare folder, delete folder, Add to folder, Create folder |  | 17
P2 | Create/View Tasks | On SRP, CV detail, Task list on Dashboard |  | 19
sign up flow in app
mailer deeplinking
open Appstore during feedback
|  | 3D touch (Long press) Call Scanner | Done
|  | Call Scanner Widget | tech
|  | Login API migrations | tech
|  | Highlight keyskills in SRP, cv detail |  | 14
|  | Training widget |  | 8
|  | Call Scanner - Show Resdex search data |  | 7
| https://infoedge.atlassian.net/browse/NIAA-19494 | Call from App notification - Rich data - CTA Actions- check feasibility |  | 4
| https://infoedge.atlassian.net/browse/NIAA-19749 | Multi scan feature |  | 5
| https://infoedge.atlassian.net/browse/NIAA-20083,https://infoedge.atlassian.net/browse/NIAA-19973 | Textual Changes- Folders | Done
| https://infoedge.atlassian.net/browse/NIAA-20591 | Suggesters Prefetch API integration |  | 20
| https://infoedge.atlassian.net/browse/NIAA-18160 | Showing Matching/All applies in JP apply inbox |  | 16
|  | concurrent sessions | Done
|  | Super user |  | 12
|  | folder listing - enhancements |  | 15
|  | push notificaiton for inactive uers |  | 0
swipe to next cv
verify OTP flow for call intent &